## Sheet1
# | Page Category | #2 | Page Template | #3 | Page Template States/Views | Description / Requirements | Duplicate of: | Design: | Asset ID
1 | Homepage | 1 | National Homepage | a | Carousel (Photo) |  |  | Complete | 6vaO9bePte8GyIi00eYygC
|  |  |  | b | Carousel (Video Thumb) |  |  | Complete | 1YYJcaYdRaEU0wEIG0M4eU
|  |  |  | c | Carousel (Video Player) |  |  | Complete | 6w9w7hppiEs8Oqymci2Eu
|  | 2 | State Homepage | a | Carousel (Photo) |  |  | Complete | kveRec2fDygceeGGO2oq0
|  |  |  | b | Carousel (Video Thumb) |  |  | Complete | 1mWMjgD9j6qgmCkkQ8wCww
|  |  |  | c | Carousel (Video Player) |  |  | Complete | 7x2XTVLRKM204yoAA84Qek
2 | News | 1 | News Listing | a | News Listing |  |  | Complete | 3gMdQgYf9m6CM80A86UWuW
|  | 2 | News Article | a | Article with Image |  |  | Complete | 6z9qCT6b1Cg2yKYwGykqoK
|  |  |  | b | Article with Embedded Video |  |  | Complete | 5U84xx5gTmmccAYmOUiWYS
|  |  |  | c | Article with Gallery |  |  | Design in Progress
3 | Events | 1 | Events Listing | a | National Events listing |  | 3.1.b | Not-required
|  |  |  | b | State Events Listing |  |  | Complete | 2SwUxDcOYgAu22EOEA68Yg
|  | 2 | Event Detail | a | Preview | Event entry has not started |  | Design in Progress
|  |  |  | b | Entry Open to anyone |  |  | Complete | 21drm5LUFWYiomOqU2W8EG
|  |  |  | c | Entry Open with Annoucement |  |  | Complete | 6GyhhoxXX2I0waCwag4KuE
|  |  |  | d | Entry Open to state members | User must be logged in to click "enter event" |  | Complete | 4OlO74js40ywaaIEIo6ga4
|  |  |  | e | Entry Closed - draw avaliable | Event entry has padded close date or is full |  | Complete | 6h1E539EWcS4mUkYSQSa2K
|  |  |  | f | Entry Closed - Results avaliable |  |  | Complete | 5j504qNwQ8OgAocMcKMQWu
|  |  |  | g | Entry Closed - Gallery enabled | Event organiser has enabled the gallery |  | Complete | 7hhz6VVrZmoIK4gWAuCGO
|  |  |  | h | Entry Closed - News enabled | Event organiser has enabled news synopsis |  | Complete | 5j504qNwQ8OgAocMcKMQWu
|  |  |  | i | Event Archived | After two weeks the event does not show up by default in listings (archived) |  | Not-required
|  | 3 | Event Log In / Sign Up | a | Open event (guest enabled) |  |  | Complete | 13rYqxzPsWcqOYsa2sEywm
|  |  |  | b | Member only event (guest disabled) |  |  | Complete | 4Q2r21Bvf28cKqA6iMCOu
|  | 4 | Event Entry Form | a | Open event (Entering Myself) |  |  | Complete | 6hjbmXtoByci88OMyk0Coe
|  |  |  | b | Open event (Entering Someone Else) |  |  | Complete | 26wpA3oqcoMmwokaUSyYa8
|  |  |  | c | Open event (Entering as guest) |  |  | Complete | 3ZUl1UxdLO6OK2a8gmiOwg
|  |  |  | d | Member only event (Entering Myself) | Email field is disabled |  | Complete | tXRHIsbsJ2mwi2SOgAso8
|  | 5 | Event Become a Member Form | a | Member Personal Details |  |  | Complete | 6q0qgxAHzUoccwwc2uyOaQ
|  |  |  | b | State specific questions / preferences |  |  | Complete | Y5SglHfxcWgYGUmKa6esK
|  |  |  | c | Viewing Terms of membership |  |  | Complete | 11PGitLhWayQ4mooQ8WEYQ
|  |  |  | d | Agreed to terms of membership | Add to order button made active |  | Complete | 1b9kOVLKleC4K0MgY4sK4C
|  | 6 | Events Summary | a | Viewing Terms and Conditions of the event |  |  | Complete | 3Lv2apNm7Sgow0yGUsS6cW
|  |  |  | b | Agreed to terms and conditions of the event | Add to cart button made active |  | Not-required
|  | 7 | Shopping Cart | a | Shopping cart with event and membership items |  | 5.4.a | Complete | 4ktSDeSN0QkQWGIwcCUo4c
|  |  |  | b | Shopping cart with only membership item | Membership can only be removed from cart once there are no other items. | 5.4.a | Design in Progress
|  | 8 | Checkout | a | Payment details | Shipping is not required for Events | 5.5.b | Complete | 5Qs1Inr1tY6AsisGOYWsgU
|  | 9 | Order Complete | a | Invoice and events summary |  | 5.6.a | Complete | 1pOORvnGPmyAM6Ec6AaI6O
4 | Ratings | 1 | National Ratings List | a | National Ratings |  | 4.2.a | Not-required
|  | 2 | State Ratings List | a | State Ratings |  |  | Complete | 39GmvNg7K8SkOeSsKeuW8s
5 | Shop | 1 | Shop Categories | a | All categories shown |  |  | Complete | 4hiFDYeqKsQGkoCiEQImiu
|  | 2 | Shop Item listing | a | List of items in a particular category |  |  | Complete | 5G5p5ShrOMG8kou4umOyWo
|  | 3 | Shop item detail | a | The item detail | User can add item to their cart |  | Complete | 6hczptTyh264kYacOaw0em
|  | 4 | Shopping Cart | a | Shopping cart with shop items |  | 3.7.a | Not-required
|  | 5 | Checkout | a | Shipping Details | When checking out items that don't require shipping this is not shown |  | Complete | 5qjfYtyIE0eIKmMmUsggCI
|  |  |  | b | Payment details |  | 3.8.a | Not-required
|  | 6 | Order Complete | a | Invoice |  |  | Complete | 4wiFs49doAY2IKwEoA0Ko4
6 | Content | 1 | About | a | About Surfing Australia / State |  |  | Complete | 5H7CNuufVSgwmoyu0WcM46
|  | 2 | Memberships | a | About memberships |  |  | Complete | 6MSWctHGdakKoq6M2ESseo
|  | 3 | Become a Member Form | a | User is not logged in - prompt to login | Users must be logged in to become a member |  | Complete | 7zBXC9VJugkowWass4U6gM
|  |  |  | b | Member Personal Details |  | 3.5.a | Complete | 5tuX90Hzva62CGc2WeycYk
|  |  |  | c | State specific questions / preferences |  | 3.5.b | Complete | SCOqPSTSUeYeIQCUMoWqo
|  |  |  | d | Viewing Terms of membership |  | 3.5.c | Complete | 6H62jdwUwgaQKGCkyiIqM8
|  |  |  | e | Agreed to terms of membership | Add to cart button made active, then checkout as per 5.5.a | 3.5.d | Complete | 4cV7YL5NXaUUA4CIU62Y4U
6 | Education | 1 | Coaching | a | About Coaching / Find a Coaching Course |  |  | Complete | 6Mo5z38PteqgW0s6Y002G
|  | 2 | Coaching Course detail | a | Preview | Course entry has not started | 3.2.a | Not-required
|  |  |  | b | Entry Open to anyone |  | 3.2.c | Complete | 53zgjMb7yMA0EWQgkusWsk
|  |  |  | c | Entry Open to state members | User must be logged in to click "enter event" | 3.2.d | Not-required
|  |  |  | d | Entry Closed | Course entry has passed close date or is full | 3.2.e | Not-required
|  | 1 | Judging | a | About Judging / Find a Judging Course |  | 6.1.a | Complete | 2UotHPduVywaQkOcY6A8Q
|  | 2 | Judging Course detail | a | Preview | Course entry has not started | 3.2.a | Not-required
|  |  |  | b | Entry Open to anyone |  | 3.2.c | Complete | 5nhtjsVEyWiOeKw6aQkgO8
|  |  |  | c | Entry Open to state members | User must be logged in to click "enter event" | 3.2.d | Not-required
|  |  |  | d | Entry Closed | Course entry has passed close date or is full | 3.2.e | Not-required
7 | MyProfile | 1 | Memberships | a | User is a member of State(s) & BRC(s) |  |  | Complete | 2vcuxG6YteAIuIAYawuYoe
|  |  |  | b | User is not a member of anything |  |  | Design in Progress
|  | 2 | Edit My Profile | a | Profile editor |  | BRC | BRC
|  | 3 | Change Password | a | Password editor |  | BRC | BRC
8 | Global | 1 | National Navigation Desktop | a | Default View |  |  | Design in Progress
|  |  |  | b | Dropdown view |  |  | Design in Progress
|  | 2 | National Navigation Mobile | a | Default View |  |  | Complete | 6OC1NkDSvY8o4W2us6oKK8
|  |  |  | b | Profile Options |  |  | Complete | 6gJdDGmQKsYSKgWMKKi2IS
|  |  |  | c | Hamburger Menu open |  |  | Complete | 32lHwM7gM0egeyysQs8CWS
|  | 3 | State Navigation Desktop | a | Default View |  |  | Design in Progress
|  |  |  | b | Dropdown view |  |  | Design in Progress
|  | 4 | State Navigation Mobile | a | Default View |  |  | Complete | TYDGdkZAsKggGQKugW6ay
|  |  |  | b | Profile Options |  | 8.2.b | Complete | 6gJdDGmQKsYSKgWMKKi2IS
|  |  |  | c | Hamburger Menu open |  |  | Complete | 6LopMQYtXy8iwIuaSGwICs
|  | 5 | National Footer | a | Footer with SA logo and state links |  |  | Design in Progress
|  | 6 | State Footer | a | Footer with state logo and no state links |  |  | Design in Progress
|  | 7 | Log In / sign up | a | Empty form |  | 3.3.b | Complete | 4Q2r21Bvf28cKqA6iMCOu
|  |  |  | b | Sign in Error |  | BRC | BRC
|  |  |  | c | Sign up complete (confirm email) |  | BRC | BRC
|  | 8 | Email Confirmed | d | Edit Your Profile |  | BRC | BRC
|  | 9 | 404 Error | a | National 404 Error |  |  | Complete | 4TCOiIQ9GocWgOKUiwcosS
|  |  |  | b | State 404 Error |  |  | Complete | 4x11zmzWvuyeIGu2IQy4KO
9 | Search | 1 | Search | a | Empty Search |  |  | Complete | A8ACFCeXduUQOYU4wy24c
|  |  |  | b | Search with results |  |  | Complete | 2dNIfSShpeySGmI6kUK0MI
|  |  |  | c | No results found |  |  | Complete | 2JjF3yPy8w0gwKAocy0sq2
10 | eDMs | 1 | Welcome / Confirm Email | a | Confirm email |  |  | BRC
|  | 2 | Order Confirmation | a | With event information |  |  | Design in Progress
|  |  |  | b | Without event information |  |  | Design in Progress
Out of Scope
Awards
Stand alone Gallery
SA Pix